Proposal Title:

Comprehensive Performance Marketing Strategy

Summary

This proposal outlines a data-driven and customer-centric performance marketing strategy leveraging Google Ads, Meta/Facebook Ads, and additional advanced advertising tools. The objective is to create, monitor, and optimize ad campaigns to achieve increased engagement, higher conversions, and maximized return on ad spend (ROAS).

The campaigns will focus on targeted goals, incorporate geofenced ad targeting, utilize Facebook's ad store location feature, and integrate Google Hotel Ads and Meta Search management. AI-powered video creation will enhance the marketing effort using client-provided videos, still images, and voiceovers to produce up to two compelling videos per month.

The approach ensures continuous adaptation to trends and campaign performance, with weekly monitoring for adjustments and monthly performance analytics to guide strategic decisions and align marketing efforts with the client’s objectives.

Phase 1: Campaign Development

Description:

This phase focuses on developing a performance marketing strategy and creating ad campaigns for Google Ads and Meta/Facebook Ads, incorporating advanced targeting features.

Assumptions:

- The client will provide access to existing advertising accounts or support creating new ones.

- Necessary video and image assets will be provided by the client for AI-assisted video creation.

Objectives:

- Establish high-performing ad campaigns tailored to client objectives.

- Incorporate features like geofenced targeting, Facebook ad store locations, and Google Hotel Ads.

- Ensure seamless integration with Meta Search platforms.

Technical Requirements:

- Access to Google Ads Manager, Meta Ads Manager, and other required platforms.

- AI video tools for creating promotional videos.

Tickets:

- Campaign Development and Setup

  - Description: Create ad campaigns, set up geofenced targeting, and enable Facebook store location ads.

  - Assigned To: Marketing Specialist

  - Estimated Time: 20 hours

- Google Hotel Ads Integration

  - Description: Set up and configure Google Hotel Ads for client properties.

  - Assigned To: Ad Operations Specialist

  - Estimated Time: 15 hours

- Meta Search Management Setup

  - Description: Integrate and configure Meta Search tools for the client.

  - Assigned To: Technical Marketing Specialist

  - Estimated Time: 12 hours

Phase 2: Campaign Monitoring and Optimization

Description:

Weekly performance monitoring and real-time optimization to enhance ROAS and conversion rates.

Assumptions:

- Performance data will be accessible from all ad platforms.

- The client agrees to regular strategy review sessions.

Objectives:

- Adjust campaigns weekly to maximize performance.

- Provide regular updates and identify opportunities for improvement.

Strategy:

- Implement A/B testing for ad creatives and targeting.

- Monitor key performance indicators (KPIs) such as click-through rates (CTR), conversion rates, and ROAS.

Tickets:

- Weekly Campaign Adjustments

  - Description: Monitor ad performance and adjust settings to improve outcomes.

  - Assigned To: Digital Marketing Specialist

  - Estimated Time: 10 hours/week (40 hours/month)

- Monthly Performance Analytics Reporting

  - Description: Prepare and deliver detailed monthly reports on ad performance with actionable insights.

  - Assigned To: Marketing Analyst

  - Estimated Time: 8 hours/month

Phase 3: AI-Powered Video Creation

Description:

Create compelling promotional videos using AI tools, combining client-provided assets with AI-generated voiceovers and visual effects.

Assumptions:

- The client will provide necessary raw video and image assets.

- AI tools will be used to enhance video quality and impact.

Objectives:

- Deliver two high-quality videos monthly to support advertising campaigns.

- Drive audience engagement and conversions through impactful storytelling.

Tickets:

- Video Production

  - Description: Develop two AI-powered videos monthly for campaigns.

  - Assigned To: Video Production Specialist

  - Estimated Time: 8 hours/video (16 hours/month)

Conclusion

This proposal delivers a performance marketing strategy that combines cutting-edge technology with customer-focused tactics. By utilizing advanced advertising features, AI-powered video content, and regular optimization, the strategy aims to achieve the client’s goals for increased engagement, higher conversions, and improved ROAS.

We look forward to partnering with you to achieve these outcomes through this structured, adaptable, and results-oriented approach.

If you'd like the Word document and XML file versions, let me know!

You said:

For this proposal what are the monthly hours on average incorporating all the work and doing this for 12 months

ChatGPT said:

To calculate the average monthly hours for the proposal, let's break down the tasks and their estimated hours across 12 months:

Phase 1: Campaign Development

- Campaign Development and Setup: 20 hours (one-time task)

- Google Hotel Ads Integration: 15 hours (one-time task)

- Meta Search Management Setup: 12 hours (one-time task)

Total Phase 1 Hours:
20 + 15 + 12 = 47 hours (one-time)

Phase 2: Campaign Monitoring and Optimization

- Weekly Campaign Adjustments: 10 hours/week = 40 hours/month

- Monthly Performance Analytics Reporting: 8 hours/month

Total Phase 2 Hours (Monthly):
40 + 8 = 48 hours/month

Phase 3: AI-Powered Video Creation

- Video Production: 8 hours/video × 2 videos/month = 16 hours/month

Total Phase 3 Hours (Monthly):
16 hours/month

Monthly Hours Calculation (Ongoing Tasks)

Phase 2 + Phase 3:
48 hours (Phase 2) + 16 hours (Phase 3) = 64 hours/month

Yearly Hours Calculation (12 Months)

- Ongoing Tasks: 64 hours/month × 12 months = 768 hours

- One-Time Tasks (Phase 1): 47 hours

Total Yearly Hours:
768 + 47 = 815 hours

Average Monthly Hours Over 12 Months

Total yearly hours ÷ 12 months = 815 ÷ 12 = ~68 hours/month